## 1) What / So what / Why / How / Who
### What
A Spring 2026 DAEN capstone delivering an Integrated Decision-Support + UX/UI prototype for community flood early warning, centered on:
- Data-as-a-Service (clean, documented, reusable data access layer)
- Risk/readiness + response decision-support (indices, prioritization, overlays)
- A mobile-friendly web dashboard (not native iOS/Android)
### So what
- Converts scattered public sensor feeds + GIS layers into actionable, defensible decision cues for communities and partners.
- Produces a reusable pipeline + catalog + playbook that can be extended semester-over-semester.
- Creates credible output for stakeholders (Gulfstream/C-RASC/USACE/STAR-TIDES) without requiring hardware work by students.
### Why now
- Capstone timeline is short (12 build weeks); scope must be locked early.
- You’re at a crossroads: multiple prior efforts exist, but the “glue” (integration + continuity) is the missing piece.
- PR deployments + USACE interest means you want an MVP that can be shown, not just talked about.
### How
- Agile scrum sprints with weekly partner meeting.
- Start with data inventory + requirements, then pipeline + baseline dashboards, then indices + prioritization, then packaging + demo.
- Keep the deliverable open-source friendly (Apache 2.0) and built on public data.
### Who
- Instructor/PM authority: Isaac (capstone delivery owner)
- Partners/SMEs: Gilberto (domain + stakeholder + continuity), Melvin (mission + community + deployment narrative), Willie (data engineering + platform integration + technical guardrails)
- Students (Team): execution of pipeline, analytics, UI, documentation
- Optional external influence: Linton/STAR-TIDES & USACE demos (only if it doesn’t pull scope)

## 2) The meeting outcome you want in 30 minutes
By the end, you want these locked:
1. Recurring meeting cadence: Thu 11:00 ET confirmed + who must attend
2. Scope statement: “data-as-a-service + decision-support dashboard (mobile-friendly web), no native mobile app, no hardware build”
3. Workstreams: either 1 team with 2 subteams or 2 teams with clean separation
4. Data access plan: where the datasets live + how students access them + continuity plan
5. Week-1 deliverables: what the team produces before next partner meeting
If you lock those, you win.

## 3) Topics to discuss (ordered, with “what to say”)
### A) Confirm scope boundaries (do this early)
Say:
- “We want a mobile-friendly dashboard experience, not native app development.”
- “Hardware is out of capstone scope; students work on public data feeds + any sensor outputs we provide.”
### B) Define the MVP deliverables in plain language
MVP =
- A working data pipeline (ETL/ELT) that pulls/normalizes selected feeds
- A data catalog + schema + provenance notes
- A decision-support dashboard showing risk/readiness and response overlays
- A minimal risk prioritization index (transparent + explainable)
### C) Decide: 1 team vs 2 teams
Offer Isaac an easy choice:
Option 1: One team, two subteams (recommended default)
- Subteam A: Data pipeline + validation + catalog
- Subteam B: UX/UI dashboard + decision cues + “playbook views”
Option 2: Two full teams (only if they truly need to place 12 students)
- Team 1: Risk/readiness indicators + prioritization (indices + reliability)
- Team 2: Response planning overlays (routes, comms, logistics layers + UI)
Key guardrail to say:
“We’ll make artifacts non-overlapping so nobody becomes a passenger.”
### D) Data inventory + continuity plan (your leadership moment)
This is where you can look the most “program-manager sharp.”
Say:
- “We’ll provide a structured dataset pack + source list, and we’ll define a storage location so future semesters don’t lose data.”
- “We’ll treat prior GitHub repos as the baseline, but we won’t assume prior datasets exist unless found.”
Propose a simple continuity plan:
- Create a “Capstone Data Pack” (versioned zip or bucket) containing:
  - curated extracts (small/medium size)
  - scripts to refresh from authoritative sources
  - README + schema + data dictionary
### E) Define “success” in Week 12
Ask Isaac to agree to 3 acceptance criteria:
1. “Data refresh is repeatable” (one-click runbook)
2. “Dashboard tells a story” (risk + response cues; not just maps)
3. “Documentation is handoff-ready” (future teams can pick up)

## 4) Proposed top-level project plan (12 build weeks)
Here’s a clean sprint sequence that matches DAEN reality.
### Sprint 0 (Week 1): Alignment + inventory
Deliverables
- MVP scope + user stories
- Data inventory + access credentials/links
- Repo setup + issue board
- Architecture sketch (pipeline → store → service → dashboard)
Dependencies
You provide: list of authoritative sources + any existing links/repos + sample datasets
### Sprint 1 (Weeks 2–3): Data foundation
Deliverables
- ETL skeleton (pull + normalize + store)
- Basic QA checks (missing data, outliers, gaps)
- Data catalog v1 (fields, units, cadence)
### Sprint 2 (Weeks 4–5): Map + baseline dashboard
Deliverables
- Baseline dashboard: layers + filters + time-series widgets
- “Known-good” minimal story: a few counties/areas as reference
### Sprint 3 (Weeks 6–7): Indicators and prioritization
Deliverables
- Risk/readiness index v1 (explainable, not deep learning)
- Reliability flags (sensor gaps, inconsistent readings)
- Prioritization logic (vulnerability + single-point-of-failure infra ideas)
### Sprint 4 (Weeks 8–9): Response decision support
Deliverables
- Response overlays: evacuation constraints, comms lines, “where help goes first”
- Scenario views: “heavy rainfall event” / “river rise” simple cases
### Sprint 5 (Weeks 10–12): Packaging + demo readiness
Deliverables
- Final report + slides + recorded demo
- Runbook (“how to refresh data, rerun pipeline”)
- Public GitHub repo polish (Apache 2.0 compatible)

## 5) Proposed deliverables list (executive-friendly)
Use these as your “contract” bullets.
1. Project charter (scope, users, success metrics)
2. Data Source Register (authoritative sources + refresh cadence)
3. Data Catalog / Dictionary
4. ETL Pipeline + QA checks
5. Decision-Support Dashboard (mobile-friendly web)
6. Risk/Readiness Index v1 (transparent, explainable)
7. Response Support Views (routes/comms/logistics overlays)
8. Runbook + Handoff Guide
9. Final presentation + poster-ready visuals

## 6) Your “leadership navigation” cheat sheet
### Things to say that signal confidence
- “Let’s lock MVP boundaries now so the team can sprint.”
- “We’ll keep it explainable—no deep learning required.”
- “Our priority is repeatability and handoff so future semesters build forward.”
### Things to avoid (scope grenades)
- “Native mobile app”
- “We’ll do tensors / deep learning”
- “We need custom hardware in the loop”
- “We’ll integrate everything everywhere”
### Questions to ask Isaac that make you look like the grown-up
1. “Do you prefer one team with subteams or two teams with separate repos?”
2. “Where should the data live for continuity (OpenStack/on-prem/HPC storage)?”
3. “What format do you want for weekly updates—demo-first or slide-first?”
4. “Any constraints on GIS tooling (ArcGIS vs open stack) for students?”

## 7) Micro-agenda for today’s 30-minute kickoff (tight)
1. 2 min – intros + confirm recurring meeting schedule
2. 5 min – MVP scope + boundaries (no native app, no hardware)
3. 8 min – workstreams + proposed sprint plan
4. 10 min – data access + continuity storage decision
5. 5 min – Week-1 tasks + next meeting agenda

## 8) Your Week-1 ask to the student team (simple and powerful)
Assign them “Day 1 wins”:
- Create repo + backlog issues (10–15)
- Create data source register (top 6–10 sources)
- Build “hello world ETL” that pulls one source and stores normalized output
- Draft dashboard wireframe (even boxes-on-a-slide is fine)